SDD OPERATING GUIDE

Integrating Spec-Driven Development into Existing ADO / Scrum Delivery

Spec Kit pilot guidance • Todo worked examples • September 2026

Purpose Help an existing Scrum team understand where SDD fits, when to use it, how to execute it without replacing normal Scrum/ADO practices, and what the Todo pilot taught us. Sections 1–13 describe the tool-agnostic operating model; Appendix A is the step-by-step walkthrough of how GitHub Spec Kit was used in the Todo pilot and accompanies the demo video (review feedback item 2).

Status Pilot guidance pending real-project validation. This is a working operating guide, not an organization-wide mandate or SLA. Revision 1.1 (6 Sep 2026): added the detailed sprint timeline with checkpoints (3.3), tooling guardrail (7), adoption plan with success criteria and onboarding (10), the future ADO ↔ Spec Kit automation concept (12), and Appendix A — the Spec Kit walkthrough for replicating the pilot — in response to review feedback.

# 1. Start Here: What Changes for an Existing Scrum Team?

The operating principle is simple: keep the delivery process the team already understands, and introduce SDD only where structured reasoning adds value.

| What remains unchanged | What SDD adds |
| --- | --- |
| ADO User Stories, Acceptance Criteria, estimation, sprint commitment, assignment and status tracking | Structured definition of expected behavior and explicit clarification of material ambiguity |
| Normal refinement, Sprint Planning, development, QA, review and PR | Technical planning, implementation breakdown and consistency/alignment checks where useful |
| BA/PO/business authority for business decisions | AI-assisted question discovery; unanswered business knowledge remains an open question |
| Existing Git branching, PR, merge and conflict practices | A shared behavioral baseline when multiple developers work on related capability |

Core rule SDD is a selective reasoning layer inside Scrum. It does not replace Scrum, ADO, Git, BA/PO authority, QA or existing governance.

# 2. When Should a Story Use SDD?

Assess suitability during normal backlog refinement. This is a team decision, not a separate approval gate.

| Good SDD signals | Normal development may be enough |
| --- | --- |
| • Material ambiguity or unanswered behavior | • Small/localized change |
| • Multiple business rules / scenarios / edge cases | • Behavior already obvious and agreed |
| • Dependencies or cross-component impact | • Little cross-component impact |
| • Meaningful architecture/design reasoning | • Low reasoning value from an additional specification |
| • High cost of assumption-driven rework or regression | • Specification overhead would exceed likely benefit |

Todo evidence SDD-selected: US-904672 Improve Todo List UX & Pagination. Intentionally normal development: Replace Todo Action Text with Icons.

# 3. End-to-End Operating Flow

## 3.1 Before Sprint Planning

1. ADO User Story: Use the approved/authoritative requirement source.

2. Backlog Refinement: Discuss behavior, dependencies, estimate readiness and SDD suitability.

3. Define expected behavior: For Spec Kit today: /speckit.specify.

4. Resolve ambiguity: For Spec Kit today: /speckit.clarify. Keep unresolved material questions explicit.

5. Business decision: BA/PO/business stakeholder answers according to existing project authority.

6. Update ADO / AC: Record authoritative decisions in the system of record.

7. Update supporting spec: Synchronize the resolved behavior.

8. SDD-assisted readiness: Story is clear enough, major material questions resolved, dependencies understood and estimable.

## 3.2 Sprint Planning and Sprint Execution

At Sprint Planning, the ready ADO story remains the unit of estimation/commitment. The supporting specification is reused; do not regenerate it simply because the story entered the sprint.

| Generic activity | Current Spec Kit reference | Purpose |
| --- | --- | --- |
| Technical design | /speckit.plan | Choose the implementation approach. |
| Implementation breakdown | /speckit.tasks | Create actionable work, preferably traceable to user-story phases. |
| Pre-implementation validation | /speckit.analyze | Check consistency across spec, plan and tasks. |
| Implementation | /speckit.implement | Build the selected scope. |
| Post-implementation alignment | /speckit.converge | Check code against intended feature behavior and remaining gaps. |
| Targeted quality checks | /speckit.checklist when useful | Use when a targeted quality gate adds value; not mandatory for every story. |

## 3.3 Indicative Timeline for a 2-Week Sprint — Proposed, Not an SLA

Days are working days relative to Sprint Planning (Day 0). The four checkpoints reuse existing ceremonies and reviews — none of them is a new meeting.

| Day | Activity | Spec Kit artifact | Who | Checkpoint |
| --- | --- | --- | --- | --- |
| −8 | Requirement identified; ADO user story written and tagged SDD-Candidate | ADO user story | BA / PO |  |
| −7 | Backlog refinement #1 — team assesses SDD suitability | — | BA + Dev + team | Suitability decision (lightweight) |
| −6 to −5 | /speckit.specify then /speckit.clarify; Outstanding Questions posted to the ADO story | spec.md, checklists | Dev + BA (AI assists) |  |
| −4 | Spec review; PO / business answers material questions | spec.md clarifications | BA / PO / QA | Checkpoint 1 — business decisions |
| −3 | ADO acceptance criteria updated; spec synchronized; story marked Ready | ADO AC + spec.md | Team | Checkpoint 2 — Definition of Ready |
| 0 | Sprint Planning — estimate and commit; developer receives the refined story + spec | — | Existing Scrum team | Sprint commitment |
| +1 to +2 | /speckit.plan → /speckit.tasks → /speckit.analyze | plan.md, tasks.md | Developer | Checkpoint 3 — technical plan review (Tech Lead) |
| +2 to +8 | /speckit.implement; converge intent ↔ code; gaps routed through change management (6.3) | code, tests | Developer (+ BA/PO if a gap is found) |  |
| +8 to +10 | QA, code review, PR merge; sprint review / demo | PR | QA / reviewers / team | Checkpoint 4 — PR approval |

Exact timing must be validated with real project teams and their existing refinement cadence; teams on a different sprint length should scale the pre-planning window to roughly one sprint.

# 4. When a Business Question Cannot Be Resolved During Refinement

AI or the refinement team may identify a material question that the BA present in the meeting cannot authoritatively answer. Do not invent or silently assume the answer.

Asynchronous clarification path Dev + BA refinement → Outstanding Question retained in spec.md → question surfaced in the corresponding ADO User Story → PO/business responds asynchronously → decision recorded in ADO/Acceptance Criteria → supporting spec updated → readiness confirmed.

Todo example: Due Date & Overdue Tracking retained questions such as when a calendar due date becomes overdue instead of guessing the rule.

Readiness rule A material unresolved business question blocks SDD-assisted readiness until the appropriate stakeholder decision is available.

# 5. User Story ↔ Spec Kit Feature Mapping

Do not enforce a mechanical 1 ADO User Story = 1 Spec Kit feature rule.

| Mapping | When to use | Todo / handling example |
| --- | --- | --- |
| 1 US → 1 feature (default) | One cohesive, independently understandable/testable capability. | US-904672 UX & Pagination. |
| Multiple US → 1 feature (allowed) | Strong capability cohesion, meaningful shared reasoning, independent story visibility, and aligned delivery window. | Complete + Delete → Todo Lifecycle Operations; separate US1/US2 visibility. |
| 1 US → multiple features (exception) | Not a normal starting model. If clarification exposes independently deliverable capabilities, return to refinement and consider splitting the ADO story. | Not observed in the pilot (recommended handling). Example: a broad Due Date Management story could split into Manage Due Dates and Reminder Notifications. |
| Simple US → no SDD feature | Small/localized story where additional specification provides little value. | Replace Todo Action Text with Icons. |

Traceability rule ADO remains authoritative for backlog, estimation, sprint, assignment and status. A Spec Kit feature should record the source ADO Story ID(s); when one feature contains multiple user-story phases, map each phase back to its ADO Story.

# 6. Multi-Developer Operating Model

## 6.1 Ownership

The specification belongs to the feature/capability and is a shared project artifact. A developer may maintain it, but business decisions remain owned by the appropriate BA/PO/business stakeholder. ADO continues to own developer assignment.

## 6.2 Branching Strategy

Developers continue using the project's normal feature-branch and PR model. For related work, start from the same reviewed/refined specification baseline before parallel implementation. Do not invent a separate SDD branching strategy.

## 6.3 Change Management

If a developer discovers a gap Classify it first. Business behavior change → raise clarification → authoritative decision → update ADO/AC → update shared spec → identify impacted Plan/Tasks/tests/code → notify impacted developers. Technical-only change → engineering decision → update plan/design if needed → notify impacted developers → continue.

## 6.4 Conflict Mechanism

| Conflict type | Resolution |
| --- | --- |
| Physical Git/code conflict | Use normal merge/rebase/PR review practices. |
| Behavior/spec conflict | Resolve what the system should do with the appropriate business/technical authority, update the shared baseline, then align implementations. |

Todo example Complete + Delete can share Todo Lifecycle Operations while ADO keeps separate story ownership. One shared feature does not mean one developer.

Key distinction: a Git conflict is not a specification conflict. When the disagreement is about what the system should do, resolve the behavior first, then align the code.

# 7. Roles and Responsibilities

| Role / system | Responsibility |
| --- | --- |
| BA / PO | Authoritative business requirement decisions and clarification according to the project's existing model. |
| Developer | Technical discovery, implementation, applicable artifact maintenance, and surfacing gaps instead of silently assuming behavior. |
| Refinement team | Collaboratively assess SDD suitability. |
| Tech Lead / Architect | Technical decisions/review where required by the existing project process. |
| QA / Tester | Use clarified behavior to derive concrete test scenarios and identify missing acceptance behavior. |
| AI / Spec Kit | Assist artifact generation, surface ambiguity, support analysis and consistency checking. |
| ADO | System of record for User Stories, Acceptance Criteria, estimation, sprint, state, assignment and tracking. |
| Git / PR | Existing code collaboration, review, integration and physical conflict management. |

Authority guardrail AI assists and proposes. It does not become the BA, PO, business stakeholder or architecture authority.

Tooling guardrail Run Spec Kit commands (/speckit.specify, /speckit.clarify, /speckit.plan, /speckit.tasks, /speckit.analyze, /speckit.implement) in GitHub Copilot Ask mode. Agent mode bypasses the Spec Kit prompts and governance, so specifications and plans generated that way should not be treated as SDD artifacts.

# 8. Worked Todo Example — UX & Pagination

ADO US-904672 — Improve Todo List UX & Pagination

| Question surfaced | Decision captured before implementation |
| --- | --- |
| What is the page size? | 10 items per page. |
| What happens when completing/deleting the last item leaves the page empty? | Automatically move to the previous valid page. |
| What pagination information is displayed? | Current page + total pages. |
| What happens for page 0, negative or beyond-last page? | Clamp to the nearest valid page. |

Why this mattered: the story initially looked implementable, but structured clarification made several behaviors explicit before coding and gave QA concrete expected outcomes.

Contrast: Replace Todo Action Text with Icons was intentionally suitable for normal development rather than a full SDD feature.

# 9. Pilot Learnings to Carry Forward

Use SDD selectively. Do not turn every story into an SDD exercise.

Clarify before coding where possible. The UX/Pagination example exposed four decisions before implementation.

AI should expose gaps, not invent business behavior. Outstanding questions stay open until the appropriate stakeholder decides.

Keep ADO authoritative. Business decisions and Acceptance Criteria remain visible in the team's existing system of record.

A shared feature does not mean one developer. ADO keeps story ownership; Git keeps normal collaboration.

Fit SDD into Scrum; do not redesign Scrum around the tool. The goal is minimum process disruption with better reasoning where it matters.

# 10. Recommended Real-Team Validation and Adoption Plan

Move from the Todo experiment to a small controlled real-project pilot rather than broad rollout.

Select suitable teams and stories: Prefer established ADO/Scrum teams with upcoming medium-complexity work and willing BA/PO/developer participation.

Run mixed normal sprints: SDD-selected and normal-development stories should coexist; do not create a separate SDD sprint.

Capture evidence: Clarification gaps, ADO/AC changes, dependencies/impacts found early, approximate SDD effort, Analyze/Converge findings, rework, carry-over reasons and team experience.

Refine guidance: Use evidence from multiple normal sprint cycles to adjust selection criteria, timing, roles and support before broader recommendation.

## 10.1 Indicative adoption timeline

| Phase | When (indicative) | Focus |
| --- | --- | --- |
| Phase 0 — Prepare | Now – September 2026 | Mani and Satish review this approach against the existing team practice (gaps, overlaps, improvements). Publish this guide, the Todo worked example and a short demo video. Provide starter constitution, templates and the suitability checklist. |
| Phase 1 — First real pilot | October 2026 (1 sprint) | One project team, 2–3 SDD-Candidate stories in a normal mixed sprint. Spec Kit SPOC pairs with the team through refinement and the sprint. Capture metrics and friction points. |
| Phase 2 — Expand and refine | November – December 2026 (2–3 sprints) | Two to three teams, including one multi-developer feature. Refine the mapping rule, timeline and change-management flow. Decide on ADO tracking fields. |
| Phase 3 — Publish | Q1 2027 | Publish guidance for broader adoption. Teams self-onboard with SPOC office hours. Evaluate the ADO ↔ Spec Kit automation concept (section 12). |

## 10.2 Success criteria (measured per SDD story)

| Criterion | Indicative target |
| --- | --- |
| Material business questions surfaced before coding | At least one per SDD story; zero answered by assumption of the developer or AI |
| ADO acceptance criteria updated before sprint commitment | 100% of SDD stories |
| Reopened / reworked stories | Lower than the team’s normal-path baseline over the pilot sprints |
| Story → Ready cycle time | Within one refinement window (about one sprint before planning) |
| Team experience | Team rates the SDD overhead as proportionate to the story; would choose it again for similar stories |

## 10.3 Onboarding approach

One-hour walkthrough using the Scrum-perspective deck and the demo video; this guide and the one-page quick reference as the reference material; the Spec Kit SPOC embedded with the team for its first sprint, then available through office hours. Teams keep their own Scrum ceremonies, ADO process and Git workflow unchanged.

Success is not 'every story uses SDD' Look for improved clarity, earlier discovery of gaps/dependencies, manageable overhead, useful traceability/alignment and minimal disruption to normal delivery.

# 11. One-Page Quick Reference

BEFORE SPRINT ADO User Story → Backlog Refinement → SDD Suitability → Define expected behavior → Clarify / Outstanding Questions → BA/PO/business decision → Update ADO/AC → Update supporting spec → SDD-assisted readiness

SPRINT Sprint Planning → Technical Plan → Tasks → Analyze → Implement → Converge → Test → Review / PR

USE SDD WHEN Ambiguity • multiple rules/scenarios • dependencies • cross-component impact • architecture/design reasoning • meaningful rework/regression risk

KEEP NORMAL DEVELOPMENT WHEN Small/localized • obvious behavior • low impact • little additional reasoning value

# 12. Future: ADO ↔ Spec Kit Automation (Concept — Not Implemented)

Implementation is not required at this stage. This section documents how automated integration could work so that the end-to-end workflow is designed with it in mind. The operating model above works fully manually.

| Step | Concept |
| --- | --- |
| 1. Trigger | An ADO user story tagged SDD-Candidate fires an ADO service hook / webhook. |
| 2. Fetch story | The ADO REST API pulls title, description, acceptance criteria and links for the story. |
| 3. Generate spec draft | A pipeline agent runs /speckit.specify (GitHub Copilot CLI) against the story to produce a draft spec.md. |
| 4. Open PR | The draft spec.md is committed on a feature branch and opened as a pull request linked to the ADO work item. |
| 5. Post questions | Outstanding Questions from spec.md are posted as ADO comments; the PO / business answers in ADO. |
| 6. Sync and track | Acceptance criteria and spec are synchronized; a Spec Status field on the work item is updated. |

## Proposed ADO tracking fields

Spec Link (URL to spec.md / feature folder), Spec Status (Draft → Clarifying → Ready → Implemented), Open Questions count (from spec.md clarifications), and traceability of FR-xxx identifiers into tasks, tests and the PR.

Automation guardrails ADO stays authoritative — automation drafts, humans decide. Business questions always route to a PO / BA and are never auto-answered. A generated spec lands as a PR for review and is never merged unattended. Progress from manual (today’s pilot) to semi-automated (fetch + draft) to automated tracking only once the manual practice is stable.

# 13. Reusable Team Package — Planned / In Progress

The reusable adoption package should contain:

SDD Operating Guide — this document, refined after real-project validation.

Todo Worked Example — actual pilot evidence and screenshots.

One-page quick reference — operating flow and selection reminders.

Short 10–15 minute walkthrough video — process-oriented, not a command-by-command tutorial.

Future ADO automation (section 12) is a separate conceptual workstream and is not a dependency for using this operating model.

# Appendix A — Walkthrough: How Spec Kit Was Used in the Todo Pilot

This appendix is the replicable, tool-specific companion to the operating model. It records what was actually done in the Todo pilot (repo TodoSDDPilotApp, ADO project EA-SDD-Experiment) so a new team can reproduce it in one sprint. Commands are GitHub Spec Kit slash commands run in GitHub Copilot Chat in VS Code (Ask mode).

## A.1 One-time setup (per repository)

| # | Step | What you get / notes |
| --- | --- | --- |
| 1 | Install the Spec Kit CLI and initialise the repo with Copilot as the agent (specify init . --ai copilot, or the team’s equivalent). | .specify/ folder with templates and scripts; .github/ prompts that expose the /speckit.* commands in Copilot Chat. |
| 2 | Run /speckit.constitution once to capture the project’s non-negotiables (coding standards, testing expectations, architecture constraints). | .specify/memory/constitution.md — every later plan is checked against it. |
| 3 | Create an ADO/ folder in the repo: ADO/refinement/sprint-N/ for exported stories, ADO/sprints/ for sprint notes. | Keeps the authoritative ADO text next to the spec so the AI reads the real story, not a paraphrase. |
| 4 | Confirm Copilot Chat is in Ask mode for Spec Kit commands. | Agent mode bypasses the Spec Kit prompts and governance (section 7). |

## A.2 Per-story walkthrough (what the pilot did for US-904672 and US-904674)

| Step | Activity / command | What happens | Pilot evidence |
| --- | --- | --- | --- |
| 1 | Export the ADO story | Copy the story title, description, acceptance criteria and tags into ADO/refinement/sprint-N/US-<id>-<title>.md. This file is the “authoritative requirement source”. | ADO/refinement/sprint-2/US-904674-Due Date & Overdue Tracking.md |
| 2 | /speckit.specify (point it at the exported story file) | Creates a numbered feature branch and specs/NNN-feature/spec.md with User Scenarios & Testing, Functional Requirements (FR-xxx), Clarifications and Outstanding Questions. The spec header records Feature Branch, Created, Status and Input source. | Branch 004-due-date-tracking; specs/004-due-date-tracking/spec.md, Input: ADO/refinement/sprint-2/US-904674… |
| 3 | /speckit.clarify | Consolidates gaps into questions and asks them one at a time with options (A / B / C / Short answer) and a recommendation; each answer is written back into spec.md before the next question. | “When should a Todo with a calendar due date become overdue?” — options A/B/C; AI recommended A. |
| 4 | Route material business questions to ADO | Questions the team cannot answer are left as Outstanding Questions in spec.md and posted on the ADO story as a comment titled “Refinement/SDD Clarification”. PO / business answers in ADO. | US-904674 comment with Q1 Overdue boundary (FR-010) and Q2 Overdue access (FR-011). US-904672 comment with Q1–Q4 pagination answers. |
| 5 | Synchronise ADO and spec; mark Ready | Update ADO acceptance criteria with the decisions; record them in the spec Clarifications section; story is Ready for Sprint Planning. | US-904672 AC now include 10 items/page, previous page on empty, clamp invalid page, show current + total pages. |
| 6 | /speckit.plan | After sprint commitment: generates plan.md (implementation approach), plus research / data-model / contracts files where relevant, checked against the constitution. | specs/003-todo-list-ux-improvement/plan.md |
| 7 | /speckit.tasks then /speckit.analyze | tasks.md — actionable tasks grouped by story phase with FR traceability; analyze checks spec ↔ plan ↔ tasks consistency before coding. | tasks.md with FR-xxx references; analyze report reviewed by the developer |
| 8 | /speckit.implement | Executes tasks phase by phase; developer reviews each phase, runs tests, commits on the normal feature branch. | Todo UX & Pagination implemented against the four clarified decisions |
| 9 | /speckit.converge, then PR | Converge compares the code to the intended behavior and lists remaining gaps; normal PR, review and QA follow. | Existing PR / review flow unchanged |
| 10 | /speckit.checklist (optional) | Targeted quality checklist for the spec or a specific concern (e.g. UX, security) where it adds value. | specs/004-due-date-tracking/checklists/requirements.md |

## A.3 Repository layout observed in the pilot

TodoSDDPilotApp/

.github/            Copilot prompts for /speckit.* commands

.specify/           templates, scripts, memory/constitution.md

ADO/refinement/sprint-2/US-904674-Due Date & Overdue Tracking.md   exported ADO stories

ADO/sprints/

specs/001-core-todo-management/

specs/002-todo-lifecycle-operations/        (Complete + Delete — shared feature)

specs/003-todo-list-ux-improvement/         (US-904672)

specs/004-due-date-tracking/spec.md, checklists/requirements.md   (US-904674)

app/  tests/  README.md

## A.4 Demo video storyboard (target 6–8 minutes)

| Scene | Shows | Talking point |
| --- | --- | --- |
| 1 | ADO backlog for EA-SDD-Experiment with SDD-Candidate tags | SDD is selective; same sprint holds both paths. |
| 2 | Exported story file and /speckit.specify producing spec.md | The AI reads the real ADO text; the spec structures it — it does not invent behavior. |
| 3 | /speckit.clarify asking the overdue-boundary question | One question at a time; material questions stay open for the PO. |
| 4 | ADO story comment “Refinement/SDD Clarification” and updated AC | ADO remains the system of record. |
| 5 | /speckit.plan, /speckit.tasks, /speckit.analyze after sprint planning | Developer consumes the refined spec; consistency check before coding. |
| 6 | /speckit.implement phase and /speckit.converge output, then the PR | Normal Git, review and QA; converge shows intent ↔ code gaps. |
| 7 | Lessons slide | Use selectively; clarify before coding; keep ADO authoritative. |

## A.5 Replication checklist for a new team

☐  Repo initialised with Spec Kit and a constitution

☐  ADO/refinement folder convention agreed

☐  SDD-Candidate tag created in the ADO project

☐  Suitability checklist used in refinement

☐  Outstanding Questions posted to ADO as “Refinement/SDD Clarification”

☐  AC updated before sprint commitment

☐  Spec Kit commands run in Copilot Ask mode

☐  Spec Kit SPOC available for the first sprint

Tool note Only this appendix is Spec Kit-specific. If the organisation standardises on a different SDD framework, replace Appendix A and the reference column in section 3.2; sections 1–13 stay as they are.