## Slide 1
Where SDD Fits in Our 2-Week Sprint
Todo pilot reference timeline • SDD enhances existing Scrum activities; it does not replace them
Existing Scrum / ADO
SDD-assisted activity
Human decision / review
SPRINT N−1 • BEFORE PLANNING
SPRINT N • EXECUTION
Day -8
Story identified
Day -7
Assess suitability
Day -6
Specify / Clarify
Day -4
PO decision
Day -3
Story ready
Day 0
Sprint planning
Day +2
Plan / Tasks / Analyze
Day +8
Implement / Converge
Day +10
QA / Review / Demo
Day
Activity (Spec Kit reference in pilot)
Artifact
Who
Checkpoint
-8
Requirement identified; ADO story written and tagged SDD candidate
ADO user story
BA / PO
-7
Backlog refinement: team assesses SDD suitability
—
BA + Dev + team
Suitability decision
-6 to -5
Define expected behavior + clarify (/speckit.specify, /speckit.clarify); questions to ADO
Feature spec (spec.md)
Dev + BA (AI assists)
-4
Spec review; PO answers material business questions
Spec clarifications
BA / PO / QA
Checkpoint 1: business decisions
-3
ADO acceptance criteria updated; spec synchronized; story marked Ready
ADO AC + spec
Team
Checkpoint 2: Definition of Ready
0
Sprint Planning: estimate and commit; refined story + spec
—
Scrum team
Sprint commitment
+1 to +2
Technical plan → task breakdown → consistency check (/speckit.plan, tasks, analyze)
Plan, task list
Developer
Checkpoint 3: technical plan review
+2 to +8
Implement; converge intent and code (/speckit.implement, converge); gaps via change management
Code, tests
Developer (+ BA/PO)
+8 to +10
QA, code review, PR merge, sprint review / demo
PR
QA / reviewers / team
Checkpoint 4: PR approval
Key takeaway: SDD starts during normal refinement and supports delivery within the sprint. Checkpoints reuse existing team reviews.